## Worksheet
Task ID | Task Description | Assigned To | Due Date | Priority | Status | Progress (%) | Notes
T-001 | Draft research proposal | Dr. Jane Smith | 2024-06-15 | High | Pending | 0%
T-002 | Collect literature review sources | Prof. Alan Torres | 2024-06-10 | High | Completed | 100% | Sources verified via university library.
T-003 | Schedule IRB approval meeting | Dr. Lisa Chen | 2024-06-25 | Medium | In Progress | 50% | Awaiting confirmation from ethics committee.
T-004 | Recruit research participants | Research Coordinator | 2024-07-15 | Medium | Pending | 0%
T-005 | Prepare preliminary data analysis plan | Dr. Raj Patel | 2024-06-30 | Low | Completed | 100% | Plan approved by statistical advisor.