## Worksheet
Task ID | Task Description | Assigned To | Due Date | Priority | Status | Progress (%) | Notes
T-001 | Review literature on AI in research | Dr. Alice Smith | 2024-06-15 | High | In Progress | 65% | Requires access to journal database
T-002 | Finalize research proposal | Dr. Robert Lee | 2024-06-25 | High | Not Started | 0% | Template attached in shared folder
T-003 | Set up data collection tools | Ms. Jane Doe | 2024-06-18 | Medium | Completed | 100% | Tools tested successfully
T-004 | Schedule ethics review meeting | Dr. Alice Smith | 2024-06-20 | Medium | In Progress | 50% | Awaiting confirmation from committee
T-005 | Analyze preliminary data | Mr. Daniel Kim | 2024-07-10 | Low | Not Started | 0% | Use SPSS v28; dataset ready