## Worksheet
Week Number | Project Name | Objective | Tasks Completed | Tasks Pending | Progress (%) | Blockers | Next Week's Focus | Notes
W1 | Data Collection | Gather survey responses from 500 participants | 324 responses collected | 176 remaining | 65% | Low response rate in region X | Follow up with non-responders via email | Survey platform glitch resolved.
W1 | Literature Review | Analyze 20 peer-reviewed papers on AI ethics | 15 papers analyzed | 5 remaining | 75% | Access to two journals restricted | Request institutional access for missing papers | Use Zotero to tag key findings.
W1 | Ethics Approval | Submit IRB documentation | Documents submitted | Awaiting review | 50% | Incomplete consent form template | Revise consent form and resubmit | Template approved by legal team.
W1 | Data Analysis Prep | Clean and structure dataset for modeling | Dataset cleaned, outliers identified | Feature engineering pending | 40% | Missing variable definitions | Collaborate with domain expert for features | Python script updated to auto-flag anomalies.
W1 | Team Sync | Conduct weekly research meeting | Meeting held, agenda followed | Action items assigned | 100% | None | Prepare Q2 timeline draft | Minutes shared via Teams.