## Worksheet
Section | Objective | Key Activities | Resources Required | Timeline (Months) | Responsible Party | Performance Metrics
1. Market Analysis | Understand market demand, competition, and customer segments. | Conduct primary and secondary research, SWOT analysis, customer surveys. | Research tools, survey platforms, data analysts. | 1–3 | Marketing & Strategy Team | Market size estimates, competitor positioning scores.
2. Resource Assessment | Evaluate internal and external resources for alignment with business goals. | Inventory audit, staff capability review, third-party vendor evaluation. | HR department, finance team, procurement unit. | 2–4 | Operations & HR Leadership | % of capacity utilization, availability of key personnel.
3. Demand Forecasting | Predict future resource needs based on sales and growth projections. | Build forecasting models, review historical data, adjust for seasonal trends. | Data analytics tools, forecasting software. | 3–5 | Finance & Planning Department | Absolute error rate (<10%), forecast accuracy over 90% of periods.
4. Budget Allocation | <Determine optimal financial distribution across departments and initiatives. | Develop budget models, perform sensitivity analysis, present to executive committee. | Financial software, access to financial reports. | 4–6 | Finance Director | Budget-to-actual variance (<5%), ROI per initiative.
5. Operational Planning | Design processes and workflows to support efficient resource utilization. | Process mapping, workflow optimization, technology integration planning. | Operations software, process engineers. | 5–7 | Operations Manager | Cycle time reduction (10%), cost per unit decrease (8%).
6. Risk & Contingency Planning | Identify potential risks and establish mitigation strategies. | Risk assessment workshops, scenario planning, contingency budgeting. | Risk management tools, legal advisory support. | 6–8 | Chief Risk Officer | Risk exposure score (<30%), contingency coverage rate (100%).
7. Implementation & Monitoring | Execute the plan and continuously monitor KPIs for adjustments. | Launch pilot programs, establish dashboards, conduct monthly reviews. | Dashboards, real-time monitoring tools, reporting team. | 8–12 | Executive Management Team | On-time delivery rate (95%), deviation from plan (<5%).