## Worksheet
Project Name | Client Name | Resource Assigned | Start Date | End Date | Status | Budget (USD) | Progress (%) | Next Milestone
Website Redesign | TechFlow Inc. | Sarah Chen, Alex Rivera | 2024-03-01 | 2024-05-31 | On Track | 15,000 | 75% | UI Mockups Approved
CRM Integration | Global Sales Hub | James Wilson, Lena Torres | 2024-03-15 | 2024-06-15 | In Progress | 8,500 | 40% | API Testing Complete
Client Onboarding | Bright Future Ltd. | Maria Gomez | 2024-04-01 | 2024-05-30 | Completed | 3,200 | 100% | Post-Implementation Review
Mobile App Development | NexaTech Solutions | David Kim, Olivia Lee | 2024-03-20 | 2024-08-31 | Planning Phase | 25,000 | 15% | Feature Requirements Finalized