## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Resource Assigned | Status th>
T001 | Project Initiation | 2024-03-15 | 2024-03-20 | 5 | Project Manager | In Progress
T002 | <Requirements Gathering | 2024-03-21 | 2024-04-15 | 35 | Business Analysts, UX Designer | Pending Approval
T003 | <System Design Phase | 2024-04-16 | 2024-05-10 | 35 | Architects, Engineers | On Track
T004 | <Development & Coding | 2024-05-11 | 2024-08-31 | 131 | Software Developers, QA Team | In Progress
T005 | <Testing & Validation | 2024-09-01 | 2024-10-15 | 45 | QA Team, Test Engineers | Scheduled
T006 | <Deployment & Go-Live | 2024-10-16 | 2024-10-3115 | DevOps, Operations Team | Pending Approval
T007 | <Post-Launch Support & Monitoring | 2024-11-01 | 2025-03-3190 | Support Team, IT Admins | Planned
© 2024 Resource Planning Gantt Chart – Advanced Template ¦ Exportable to Excel Format