## Worksheet
Task | Start Date | End Date | Duration (Days) | Resource | Status | Dependencies
Project Initiation | 2024-03-01 | 2024-03-07 | 7 | Project Manager | On Track | None
Market Analysis | 2024-03-08 | 2024-03-25 | 18 | Market Research Team | On Track | Project Initiation
Product Design | 2024-03-26 | 2024-04-15 | 21 | Design Team | Planned | Market Analysis
Development Phase | 2024-04-16 | 2024-06-15 | 61 | Engineering Team | On Track | Product Design
Testing & Quality Assurance | 2024-06-16 | 2024-07-10 | 25 | QA Team | On Track | Development Phase
Deployment & Launch | 2024-07-11 | 2024-07-31 | 31 | Operations Team | Planned | Testing & Quality Assurance