## Gantt Chart - Resource Planning
Task ID | Task Name | Start Date | End Date th> | Status | Resource
T101 | Project Initiation | 2024-03-01 | 2024-03-15 | In Progress | Project Manager
T102 | <Requirement Gathering | 2024-03-16 | 2024-04-10 | Pending | Business Analysts
T103 | Design Phase | 2024-04-11 | 2024-05-30 | Planned | UI/UX Team
T104 | Development Phase | 2024-06-01 | 2024-08-31 | Not Started | Developers Team
T105 | Testing & QA | 2024-09-01 | 2024-10-15 | Pending | QA Engineers
T106 | Deployment & Training | 2024-10-16 | 2024-11-30 | Not Started | Operations Team