## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status | Dependencies
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | Project Manager | Completed | None
Resource Assessment | 2024-01-16 | 2024-02-05 | 20 | HR Director | In Progress | Project Initiation
Budget Finalization | 2024-02-06 | 2024-02-15 | 10 | Finance Officer | Pending | Resource Assessment
Team Deployment | 2024-02-16 | 2024-03-10 | 25 | Operations Lead | Not Started | Budget Finalization
Performance Review & Adjustment | 2024-03-11 | 2024-03-31 | 21 | Project Manager | Planned | Team Deployment