## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team | Status | Progress (%)
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Project Office | Completed | 100%
Resource Assessment | 2024-03-16 | 2024-04-10 | 35 | HR & Operations | In Progress | 70%
Budget Planning | 2024-04-11 | 2024-05-05 | 35 | Finance Team | Not Started | 0%
Team Training & Onboarding | 2024-05-06 | 2024-06-15 | 40 | Training Department | Not Started | 0%
Execution Phase (Q3) | 2024-06-16 | 2024-09-30 | 115 | Project Execution Team | Not Started | 0%
Review & Optimization | 2024-10-01 | 2024-10-31 | 31 | Project Management Office | Not Started | 0%