## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team | Status | Progress (%)
Requirement Analysis | 2024-03-01 | 2024-03-15 | 15 | Product Planning Team | Completed | 100%
System Design | 2024-03-16 | 2024-04-10 | 35 | Engineering Team | In Progress | 65%
Development Phase | 2024-04-11 | 2024-06-30 | 81 | Development Team | Not Started | 0%
Testing & QA | 2024-07-01 | 2024-08-15 | 65 | QA & DevOps Team | Not Started | 0%
Deployment & Launch | 2024-08-16 | 2024-08-31 | 16 | Operations Team | Not Started | 0%