## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Resource | Progress (%) | Status
R-001 | Resource Assessment & Inventory Review | 2024-03-15 | 2024-03-25 | 10 | HR Team, Finance Dept. | 85% | On Track
R-002 | Team Capacity Planning | 2024-03-26 | 2024-04-10 | 15 | Operations Manager, IT Team | 60% | On Track
R-003 | Procurement of Equipment & Tools | 2024-04-11 | 2024-05-15 | 35 | Purchasing Team, Logistics | 30% | Delayed
R-004 | Training & Skill Development Plan | 2024-05-16 | 2024-06-30 | 45 | L&D Department, Supervisors | 15% | Planning
R-005 | Final Resource Allocation & Approval | 2024-07-01 | 2024-07-15 | 15 | C-level Leadership, Finance | 0% | Not Started