## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Resource Group | Dependencies | Milestone? | Priority | Status | Progress (%) | Budget (USD) | Actual Start Date | Actual End Date
RPL-001 | Project Initiation & Planning | 2024-03-01 | 2024-03-15 | 15 | Jane Doe | Project Management |  | Yes | High | On Track | 100% | 50,000.00
RPL-002 | Requirements Gathering & Analysis | 2024-03-16 | 2024-04-15 | 30 | Mark Smith | Business Analysts | RPL-001 | No | High | On Track | 85% | 60,000.00
RPL-003 | System Design & Architecture | 2024-04-16 | 2024-05-31 | 46 | Lisa Chen | Engineering Team | RPL-002 | No | Medium | On Track | 75% | 80,000.00
RPL-004 | Development & Coding | 2024-06-01 | 2024-08-31 | 90 | Team A & B | Software Developers | RPL-003 | No | High | Planning | 20% | 150,000.00
RPL-005 | Testing & Quality Assurance | 2024-09-01 | 2024-10-15 | 45 | David Lee | QA Team | RPL-004 | No | High | Not Started | 0% | 75,000.00
RPL-006 | Deployment & Go-Live | 2024-10-16 | 2024-10-31 | 15 | Sarah Kim | Operations Team | RPL-005 | Yes | High | On Track | 100% | 30,000.00