## Worksheet
Task | Start Date | End Date | Duration (Days) | Assigned To | Status | Progress (%)
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | John Doe | Completed | 100%
Resource Assessment & Planning | 2024-03-02 | 2024-03-10 | 9 | Jane Smith | In Progress | 65%
Team Training & Onboarding | 2024-03-11 | 2024-03-25 | 15 | Alex Brown | Not Started | 0%
Requirement Gathering Workshop | 2024-03-26 | 2024-04-05 | 10 | Maria Garcia | Planned | 0%
Budget Finalization & Approval | 2024-04-06 | 2024-04-15 | 10 | David Lee | Pending Approval | 0%
Development Phase - Sprint 1 | 2024-04-16 | 2024-05-15 | 30 | Team A (5 members) | Not Started | 0%