## Worksheet
Task ID | Task Name | Start Date | End Date th> | Duration (Days) | Resource(s) | Dependencies | Priority | Status | Progress (%)
RPL-001 | Initiate Resource Planning Process | 2024-03-01 | 2024-03-15 | 15 | Project Manager, HR Lead | None | High | Planned | 100%
RPL-002 | Conduct Resource Audit | 2024-03-16 | 2024-03-31 | 26 | HR Analyst, Finance Officer | RPL-001 | Medium | In Progress | 65%
RPL-003 | Define Resource Requirements | 2024-04-01 | 2024-04-15 | 15 | Operations Director, Planning Team | RPL-002 | High | Not Started | 0%
RPL-004 | Allocate Resources to Projects | 2024-04-16 | 2024-05-31 | 56 | All Project Managers, HR Team | RPL-003 | Critical | Planned | 20%
RPL-005 | Monitor and Adjust Resource Utilization | 2024-06-01 | 2024-07-31 | 83 | Resource Manager, Performance Team | RPL-004 | Medium | Not Started | 0%