## Worksheet
Task | Start Date | End Date | Duration (Days) | Budget (USD) | Resource Allocation | Progress (%) | Cost Variance
Market Research & Analysis | 2024-03-01 | 2024-03-15 | 15 | 15,000 | 3 Analysts | 90% | 200
Product Development Phase 1 | 2024-03-16 | 2024-05-31 | 77 | 185,000 | 6 Developers + 2 Designers | 65% | -3,200
Pilot Testing & Validation | 2024-06-01 | 2024-07-15 | 46 | 75,000 | 4 Testers + 1 Manager | 85% | 800
Full-Scale Production Setup | 2024-07-16 | 2024-09-30 | 75 | 310,000 | 8 Engineers + 3 Operators | 40% | -12,500
Launch & Marketing Campaign | 2024-10-01 | 2024-11-30 | 60 | 95,000 | 5 Marketers + 2 SMM | 70% | +1,100