## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | John Doe | Completed
Resource Assessment | 2024-03-06 | 2024-03-15 | 10 | Jane Smith | In Progress
Workforce Scheduling | 2024-03-16 | 2024-03-25 | 10 | Mike Johnson | Planned
Budget Allocation | 2024-03-26 | 2024-04-03 | 8 | Sarah Lee | Pending
Final Review & Approval | 2024-04-04 | 2024-04-10 | 7 | David Kim | Not Started