## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Resources | Status th>
RPL-001 | Market Research & Analysis | 2024-03-15 | 2024-03-31 | 16 | Marketing Team, Data Analysts | In Progress
RPL-002 | Product Roadmap Development | 2024-04-01 | 2024-04-15 | 15 | Product Managers, UX Designers | On Schedule
RPL-M1 | Q2 Product Launch Review | 2024-04-20 | 2024-04-20 | 1 | All Teams | Milestone Reached
RPL-003 | Development Phase (Phase 1) | 2024-04-21 | 2024-05-31 | 51 | Engineering Team, QA Engineers | In Progress
RPL-004 | Internal Testing & Feedback Loop | 2024-06-01 | 2024-06-15 | 15 | QA Team, Customer Support | Pending Start
RPL-M2 | Pre-Launch Training Session | 2024-06-20 | 2024-06-20 | 1 | Sales, Marketing, Customer Service | Pending Approval
RPL-005 | Final Product Launch | 2024-07-01 | 2024-07-15 | 15 | All Departments | Planned