## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Manager | Status | Progress (%)
RPL-001 | Resource Demand Forecasting | 2024-03-15 | 2024-03-25 | 11 | M. Johnson | On Track | 95%
RPL-002 | Team Capacity Allocation | 2024-03-26 | 2024-04-10 | 15 | S. Lee | In Progress | 60%
RPL-003 | Equipment and Tooling Scheduling | 2024-04-11 | 2024-04-25 | 15 | T. Kim | Not Started | 0%
RPL-004 | Training Schedule Finalization | 2024-04-26 | 2024-05-15 | 21 | A. Patel | Planned | 0%
RPL-005 | Performance Review & Adjustment | 2024-05-16 | 2024-05-31 | 16 | M. Johnson | Not Started | 0%