## Worksheet
Resource Planning Gantt Chart
Task ID | Task Name | Start Date | End Date th> | Duration (Days) | Resource Assignments | Status
#RPL-001 | Project Initiation & Planning | 2024-03-01 | 2024-03-15 | 15 | Project Manager, Finance Lead | On Track
#RPL-002 | Resource Requirements Analysis | 2024-03-16 | 2024-04-05 | 21 | Data Analyst, HR Lead | Completed
#RPL-003 | Team Scheduling & Allocation | 2024-04-06 | 2024-04-18 | 13 | Scheduling Officer, Operations Lead | In Progress
#RPL-004 | Equipment & Tool Procurement | 2024-04-19 | 2024-05-15 | 28 | Purchasing Manager, Logistics Officer | Planned
#RPL-005 | Training & Onboarding Plan | 2024-05-16 | 2024-06-10 | 35 | Training Coordinator, HR Manager | Pending Approval
#RPL-006 | Workforce Capacity Assessment | 2024-06-11 | 2024-07-15 | 35 | Operations Manager, HR Director | Scheduled
#RPL-007 | Process Optimization Workshops | 2024-07-16 | 2024-08-15 | 31 | Process Engineer, Department Heads | Not Started
#RPL-008 | Milestone Review & Adjustment Phase | 2024-08-16 | 2024-10-31 | 76 | Project Manager, Steering Committee | Planned
#RPL-009 | Final Resource Allocation Report | 2024-11-01 | 2024-11-30 | 30 | Senior Manager, Finance & Operations | To Be Finalized
#RPL-010 | Post-Implementation Review Meeting | 2024-12-01 | 2024-12-05 | 5 | Project Manager, Customer Success Lead | Scheduled
#RPL-011 | Resource Pooling Strategy Development | 2024-03-25 | 2024-05-31 | 78 | Strategic Planner, IT Director | In Review
#RPL-012 | Contingency Planning for Staff Shortfalls | 2024-06-01 | 2024-07-30 | 61 | Risk Analyst, HR Officer | Pending Review
#RPL-013 | Vendor & Outsourcing Evaluation Plan | 2024-08-01 | 2024-10-31 | 93 | Purchasing Officer, Legal Advisor | In Progress
#RPL-014 | Skill Gap Analysis & Upskilling Program | 2024-11-01 | 2025-01-31 | 93 | L&D Manager, HR Director | Planned for Q4 2024
#RPL-015 | Annual Resource Forecasting & Review | 2025-02-01 | 2025-03-31 | 61 | Fiscal Analyst, Operations Manager | To Be Scheduled
Prepared for Resource Planning - Multi-Page Gantt Chart ¦ Version 2.1 ¦ © 2024