## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Resource Allocation | Status
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Jane Doe | Project Manager, HR | On Track
Market Research | 2024-03-06 | 2024-03-15 | 10 | John Smith | Marketing Team | On Track
Product Design | 2024-03-16 | 2024-04-10 | 35 | Lisa Chen | Design Team | In Progress
Development Phase | 2024-04-11 | 2024-06-30 | 91 | Mike Johnson | Engineering Team | Planned
Testing & QA | 2024-07-01 | 2024-07-31 | 31 | Sarah Lee | QA Team | Not Started
Deployment & Launch | 2024-08-01 | 2024-08-15 | 15 | David Kim | IT Operations | Planned