## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 days | John Smith | Completed
Resource Assessment | 2024-03-16 | 2024-04-05 | 21 days | Sarah Lee | In Progress
Budget Planning | 2024-04-06 | 2024-04-20 | 15 days | Michael Brown | Planned
Team Deployment | 2024-04-21 | 2024-05-10 | 21 days | Lisa Chen | Pending Approval
Risk Analysis & Mitigation | 2024-05-11 | 2024-05-31 | 21 days | David Wilson | Not Started
Final Review & Sign-off | 2024-06-01 | 2024-06-15 | 15 days | Project Manager | Scheduled