## Worksheet
Task | Start Date | End Date | Duration (Days) | Resource(s) | Dependencies | Status
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | Project Manager, Business Analyst | None | On Track
Resource Assessment | 2024-01-16 | 2024-02-05 | 20 | HR Team, Operations Lead | After Initiation | On Track
Requirement Gathering | 2024-02-06 | 2024-03-15 | 40 | Business Analysts, Stakeholders | After Assessment | In Progress
Design Phase | 2024-03-16 | 2024-05-10 | 65 | Design Team, UX Specialists | After Requirements | Planned
Development Phase | 2024-05-11 | 2024-08-31 | 130 | Development Team, QA Engineers | After Design | Not Started
Testing & Validation | 2024-09-01 | 2024-10-15 | 45 | QA Team, Testing Leads | After Development | Not Started
Deployment & Training | 2024-10-16 | 2024-11-30 | 45 | IT Team, End Users | After Testing | Not Started