## Worksheet
Activity | Start Date | End Date | Duration (Days) | Quarter | Responsible Team | Status
Market Research & Analysis | 2024-01-01 | 2024-03-31 | 90 | Q1 | Strategy & Planning | On Track
Product Roadmap Development | 2024-03-01 | 2024-06-30 | 120 | Q2 | Product Management | In Progress
Resource Allocation Planning | 2024-04-15 | 2024-07-31 | 105 | Q2 | HR & Operations | Pending Approval
Budget Forecasting & Review | 2024-05-01 | 2024-08-31 | 120 | Q3 | Finance Team | Scheduled
Team Training & Onboarding | 2024-06-15 | 2024-09-30 | 90 | Q3 | HR & Learning | Planning Stage
Quarterly Performance Review | 2024-09-01 | 2024-10-31 | 60 | Q4 | Executive Leadership | Not Started