## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Resource Assessment | 2024-03-01 | 2024-03-15 | 15 | HR Department | On Track
Team Formation | 2024-03-16 | 2024-04-05 | 21 | Project Manager | In Progress
Budget Allocation | 2024-04-06 | 2024-04-15 | 10 | Finance Team | Completed
Equipment Procurement | 2024-04-16 | 2024-05-10 | 35 | Procurement Officer | Planned
Training & Onboarding | 2024-05-11 | 2024-06-01 | 31 | Training Lead | Scheduled