## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Resource Requirement Analysis | 2024-03-01 | 2024-03-15 | 15 | Project Manager | Completed
Budget Allocation Plan | 2024-03-16 | 2024-03-31 | 16 | Finance Team | In Progress
Team Capacity Assessment | 2024-04-01 | 2024-04-10 | 10 | HR Department | Not Started
Equipment Procurement | 2024-04-11 | 2024-05-15 | 35 | Procurement Officer | Planned
Training & Onboarding Schedule | 2024-05-16 | 2024-06-05 | 21 | Training Coordinator | Not Started