## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Market Research | 2024-03-01 | 2024-03-15 | 15 | Jane Doe | On Track
Product Design | 2024-03-16 | 2024-04-10 | 35 | John Smith | In Progress
Prototype Development | 2024-04-11 | 2024-05-05 | 35 | Mike Lee | Not Started
Pilot Testing | 2024-05-06 | 2024-05-31 | 26 | Sarah Brown | Planned
Launch Preparation | 2024-06-01 | 2024-06-30 | 30 | Team Lead | Not Started