## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Resource Assigned | Status | Progress %
RP-001 | Market Research Phase | 2024-03-15 | 2024-03-25 | 11 | Marketing Team | On Track | 95%
RP-002 | <Product Requirement Specification | 2024-03-26 | 2024-04-10 | 15 | Product Manager, Engineers | On Track | 80%
RP-003 | Resource Allocation Planning | 2024-04-11 | 2024-04-18 | 8 | HR, Finance Team | In Progress | 50%
RP-004 | Development Sprint Planning | 2024-04-19 | 2024-05-15 | 27 | Engineering Team | Not Started | 0%
RP-005 | Quality Assurance & Testing | 2024-05-16 | 2024-06-10 | 35 | QA Team, DevOps | Planned | 0%