## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Project Management Team | Completed
Resource Assessment | 2024-03-16 | 2024-04-05 | 21 | HR & Operations Team | In Progress
Workforce Allocation | 2024-04-06 | 2024-04-30 | 25 | Resource Planning Team | Planned
Budget Forecasting | 2024-05-01 | 2024-05-15 | 15 | Finance Team | <Pending
Timeline Finalization | 2024-05-16 | 2024-06-05 | 21 | Project Management Team | Not Started