## Worksheet
Task Name | Start Date | End Date | Duration (Days) | Resource Assigned | Status | Dependencies
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | Priya Sharma | On Track
Resource Planning & Allocation | 2024-01-162024-02-1530 | James Lee, Maria Gonzalez | On Track | Project Initiation
Budget Finalization & Approval | 2024-02-162024-03-1530 | Anna Patel, Robert Kim | On Track | Resource Planning & Allocation
Procurement of Materials | 2024-03-162024-05-1560 | Luis Mendez, Sofia Nguyen | Planning Phase | Budget Finalization & Approval
Implementation & Deployment | 2024-05-162024-07-3186 | All Team Members | On Track | Procurement of Materials
Total Duration (Days) | 241