## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status | Progress (%) | Dependencies
RPL-001 | Resource Demand Analysis | 2024-03-15 | 2024-03-20 | 5 | Alice Johnson | On Track | 100%
RPL-002 | Team Capacity Assessment | 2024-03-21 | 2024-03-28 | 7 | Bob Smith | In Progress | 65% | RPL-001
RPL-003 | Resource Allocation Plan | 2024-03-29 | 2024-04-10 | 12 | Carol Davis | Not Started | 0% | RPL-002
RPL-004 | Performance Monitoring Setup | 2024-04-11 | 2024-04-18 | 7 | David Lee | On Track | 90%
RPL-005 | Review & Finalize Resource Plan | 2024-04-19 | 2024-04-25 | 6 | Eva Martinez | Not Started | 0% | RPL-003, RPL-004