## Worksheet
Resource | Task Description | Assigned To | Start Date | End Date | Status | Budget Allocation (USD) | Actual Spend (USD)
Software Developer | Development of API integration module | Jane Smith | 2024-03-15 | 2024-04-15 | In Progress | 3,500.00 | 2,850.00
Project Manager | Client requirement review and planning | Mark Johnson | <+24-03-102024-04-10 | Planned | 1,800.00 | 1,800.00
UI/UX Designer | Wireframe and mockup design for dashboard | Sarah Lee | 2024-03-20 | 2024-04-15 | Completed | 1,200.00 | 1,200.00
Data Analyst | Monthly performance data analysis | David Wong | 2024-03-18 | 2024-04-18 | In Progress | 2,300.00 | 1,560.00