## Worksheet
Monthly Resource Planning Dashboard
Month: January 2024
Resource | Work Packages |  |  | Team & Capacity
| WP1 - Project Launch | WP2 - System Integration | WP3 - Training Rollout | Assigned Team | Avg. Hours/Week | Status (On Track?)
Development Team A | Active (80%) | Pending Review | Active (90%) | 40 | Yes
QA & Testing Group | Pending Start | Active (75%) | Cross-Functional (60%) | 30 | No (Delay)
Training & Support Staff | <On Hold | Active (100%) | Support Team Only | 25 | Yes
Summary |  |  | Total Assigned Hours/Week: 95 | Overall Progress: 82% | Key Risks Identified: 2
Notes & Recommendations:
• Ensure QA team schedule alignment with development milestones. • Recommend additional training support for new system modules. • Monitor resource burnout indicators in week 4.