## Worksheet
Order ID | Resource Name | Required Quantity | Planned Start Date | Planned End Date | Status | Assigned To | Priority Level | Notes
ORD-2024-001 | Server Rack (Model X5) | 15 | 2024-04-15 | 2024-05-30 | On Track | John Doe | High | Critical for new data center rollout.
ORD-2024-002 | Power Supply Unit (PSU) | 50 | 2024-04-20 | 2024-05-10 | In Progress | Jane Smith | Medium | Delay expected due to supplier backlog.
ORD-2024-003 | Network Switch (Model NS7) | 8 | 2024-05-01 | 2024-06-15 | Pending Approval | - | High | Awaiting budget sign-off from Finance.
ORD-2024-004 | Cable Management System | 20 | 2024-04-30 | 2024-05-15 | On Track | Alex Chen | Low | Standard configuration, no special requirements.