## Worksheet
Order ID | Resource Name | Requested Date | Priority Level | Status | Assigned To | Estimated Completion | Actual Completion | Action Required
ORD-2023-001 | Server Rack Unit (SRU-7) | 2023-10-15 | High | In Progress | Alex Morgan | 2023-11-05 |  | Review delivery timeline
ORD-2023-002 | Network Switch (SW-95) | 2023-10-18 | Medium | Pending Approval | Sarah Chen | 2023-11-10 |  | Submit for budget sign-off
ORD-2023-003 | Cloud Storage Tier (CST-X) | 2023-10-20 | High | Approved | David Kim | 2023-11-03 | 2023-11-03 | No action required
ORD-2023-004 | Backup Power Unit (BPU-3) | 2023-10-25 | Critical | On Hold | James Reed | 2023-11-20 |  | Check supplier availability
Resource Planning - Order Tracker ¦ Dashboard View