## Worksheet
Order ID | Resource Name | Requested Date | Planned Start Date | Planned End Date | Status | Assigned To | Priority | Current Progress (%) | Remarks
ORD-2024-001 | Server Rack Unit (SRU-5) | 2024-03-15 | 2024-03-20 | 2024-03-31 | In Progress | John Smith | High | 65% | Delivery delayed due to supplier issues.
ORD-2024-002 | Network Switch (SW-7X) | 2024-03-18 | 2024-03-25 | 2024-04-05 | Pending Approval | Maria Lopez | Medium | 0% | Awaiting IT Director sign-off.
ORD-2024-003 | Firewall Module (FW-V9) | 2024-03-16 | 2024-03-28 | 2024-04-10 | Approved | David Chen | High | 40% | Installation scheduled for next week.
ORD-2024-004 | Backup Storage Array (BSA-3) | 2024-03-19 | 2024-04-01 | 2024-04-15 | On Hold | Sarah Kim | Medium | 0% | Budget reallocation pending.