## Worksheet
Order Number | Resource Name | Required Date | Planned Delivery Date | Status | Assigned To | Priority Level | Notes
ORD-2023-001 | Server Rack Unit (Model X9) | 2023-10-15 | 2023-10-25 | In Progress | John Smith | High | Needs delivery before server migration.
ORD-2023-002 | Network Switch (Model N15) | 2023-11-01 | 2023-11-08 | Pending Approval | Jane Doe | Medium | Waiting for IT Director approval.
ORD-2023-003 | Firewall Appliance (Model F7) | 2023-11-15 | 2023-11-28 | On Hold | Mike Johnson | High | Awaiting budget confirmation from Finance.
ORD-2023-004 | Backup Storage Array (Model B5) | 2023-11-30 | 2023-12-10 | Approved | Sarah Lee | Low | Standard deployment; no urgent requirements.