## Worksheet
Order ID | Resource Name | Required Date | Planned Start Date | Planned End Date | Current Status | Assigned To | Progress (%) | Notes
ORD-2024-001 | Server Cluster A | 2024-05-15 | 2024-05-18 | 2024-05-31 | In Progress | Jane Smith | 65% | Testing phase ongoing.
ORD-2024-002 | Data Backup System | 2024-06-10 | 2024-06-15 | 2024-06-30 | Pending Approval | Mark Johnson | 0% | Waiting for budget sign-off.
ORD-2024-003 | Cold Storage Unit | 2024-07-052024-07-10 | 2024-07-18 | On Hold | Lisa Chen | 15% | Site relocation delay.
ORD-2024-004 | Network Expansion | 2024-08-15 | 2024-08-20 | 2024-09-15 | Not Started | David Brown | 0% | Design phase pending.