## Worksheet
Week | Task | Responsible Team Member | Start Date | End Date | Resources Required | Status | Notes
Week 1 | Project Kickoff Meeting | Project Lead & Team Manager | 2024-04-01 | 2024-04-05 | Meeting Room, Laptop, Project Documents | Completed | All team members present and aligned.
Week 2 | Requirement Gathering | Product & UX Team | 2024-04-08 | 2024-04-15 | Stakeholders, Survey Tools, Notebooks | In Progress | Finalizing stakeholder feedback.
Week 3 | Design Mockups Approval | UI/UX Team | 2024-04-16 | 2024-04-22 | Design Software, Feedback Forms | Pending Approval | Awaiting review from Product Manager.
Week 4 | Development Sprint Planning | Engineering Team | 2024-04-23 | 2024-05-01 | Laptops, Version Control System, Jira Setup | Planned | Initial sprint tasks assigned.
Week 5 | Quality Assurance Testing | QA Team | 2024-05-06 | 2024-05-13 | Test Environment, Test Cases, Bug Tracking Tool | Not Started | Waiting for development completion.