## Worksheet
Task ID | Task Name | Responsible Person | Start Date | End Date | Duration (Days) | Resource Required | Priority | Status | Dependencies
P-001 | Project Initiation & Feasibility Study | Jane Smith | 2024-03-15 | 2024-03-25 | 11 | Project Manager, Business Analyst | High | In Progress | None
P-002 | Requirements Gathering & Analysis | Alex Johnson | 2024-03-26 | 2024-04-10 | 15 | Business Analyst, Stakeholders | High | Not Started | P-001
P-003 | Solution Design & Architecture Planning | Sam Rivera | 2024-04-11 | 2024-05-05 | 25 | System Architect, Developers | Medium | Planned | P-002
P-004 | Development & Coding Phase | Team A - Devs | 2024-05-06 | 2024-07-15 | 60 | Software Developers, QA Engineers | High | Not Started | P-003
P-005 | Testing & Quality Assurance | Lisa Chen | 2024-07-16 | 2024-08-05 | 19 | QA Team, Testers | High | Not Started | P-004
P-006 | Deployment & Go-Live | Mark Thompson | 2024-08-06 | 2024-08-15 | 10 | IT Operations, Support Team | Critical | Not Started | P-005