## Worksheet
Task | Responsible | Start Date | End Date | Duration (Days) | Status | Resources Required
Project Initiation | Project Manager | 2024-03-01 | 2024-03-05 | 5 | In Progress | 1 Full-Time
Requirements Gathering | Business Analyst | 2024-03-06 | 2024-03-15 | 10 | On Track | 2 Full-Time
Design Phase | UX Designer & Developer | 2024-03-16 | 2024-04-10 | 35 | Planned | 3 Full-Time
Development | Software Engineers | 2024-04-11 | 2024-06-15 | 75 | On Track | 6 Full-Time
Testing & QA | QA Team | 2024-06-16 | 2024-07-10 | 35 | Completed | 4 Full-Time
Deployment & Go-Live | IT Operations | 2024-07-11 | 2024-07-15 | 5 | Completed | 2 Full-Time
Post-Implementation Review | Project Manager | 2024-07-16 | 2024-07-20 | 5 | Not Started | 1 Full-Time