## Worksheet
Task | Responsible Party | Start Date | End Date | Duration (Days) | Resource Required | Budget (USD) | Status | Priority
Project Initiation | Project Manager | 2024-03-01 | 2024-03-15 | 15 | Project Manager, Legal Advisor | 10,000 | On Track | High
Requirements Gathering | Business Analysts | 2024-03-16 | 2024-04-10 | 35 | Business Analysts, Stakeholders | 15,000 | On Track | High
Design Phase | UX & Systems Design Team | 2024-04-11 | 2024-05-05 | 35 | Designers, Developers | 25,000 | On Track | Medium
Development Phase | Software Development Team | 2024-05-06 | 2024-07-15 | 70 | Developers, QA Engineers | 80,000 | On Track | High
Testing & Quality Assurance | QA Team | 2024-07-16 | 2024-08-10 | 35 | QA Engineers, Test Tools | 12,000 | On Track | Medium
Deployment & Go-Live | IT Operations, Project Manager | 2024-08-11 | 2024-08-15 | 5 | IT Team, Cloud Services | 8,000 | On Track | High
Post-Implementation Review | Project Manager, Stakeholders | 2024-08-16 | 2024-08-20 | 5 | Project Manager, Feedback Team | 5,000 | Pending | Low