## Worksheet
Task | Responsible | Start Date | End Date | Duration | Resource Type | Status
Project Initiation | Project Manager | 2024-03-01 | 2024-03-15 | 15 days | Human | Planned
Resource Assessment | Operations Lead | 2024-03-16 | 2024-03-31 | 25 days | Human & Tech | In Progress
Budget Allocation | Finance Officer | 2024-04-01 | 2024-04-10 | 10 days | Financial | Planned
Team Training & Onboarding | HR Director | 2024-04-11 | 2024-05-05 | 35 days | Human | Not Started
Project Execution Phase | Project Manager | 2024-05-06 | 2024-07-31 | 96 days | Human & Tech | Planned