## Worksheet
Task ID | Task Name | Responsible Person | Start Date | End Date | Duration (Days) | Resource Required | Priority | Status
PR-001 | Project Initiation & Approval | John Doe | 2024-03-01 | 2024-03-15 | 15 | Project Manager, Legal Advisor | High | In Progress
PR-002 | Resource Allocation & Team Setup | Sarah Kim | 2024-03-16 | 2024-04-10 | 25 | HR, IT Support, Finance Team | High | Not Started
PR-003 | Scope Definition & Requirements Gathering | Mike Thompson | 2024-04-11 | 2024-05-15 | 35 | Business Analysts, Stakeholders | Medium | Planned
PR-004 | Development Phase - Design & Prototyping | Linda Patel | 2024-05-16 | 2024-07-31 | 76 | Design Team, Developers | High | In Progress
PR-005 | Testing & Quality Assurance | David Lee | 2024-08-01 | 2024-09-15 | 45 | QA Team, External Auditor | High | Not Started
Total Tasks | Project Summary | Key Resources | Critical Path Duration | Overall Status