## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Resource Required | Status | Priority
Project Initiation & Feasibility Study | Alex Morgan | 2024-03-15 | 2024-03-25 | 11 | Project Manager, Business Analyst | On Track | High
Requirements Gathering & Analysis | Samira Patel | <2024-03-26 | 2024-04-10 | 15 | Business Analyst, Stakeholders | In Progress | High
Design Phase – UI/UX Prototyping | Jordan Lee | 2024-04-11 | 2024-04-25 | 15 | UI/UX Designer, Product Owner | Planned | Medium
Development Phase – Backend Implementation | Marcus Reed | 2024-04-26 | 2024-06-15 | 60 | Senior Developer, DevOps Engineer | Not Started | High
Development Phase – Frontend Implementation | Lena Chen | 2024-05-01 | 2024-06-15 | 60 | Frontend Developer, QA Engineer | Not Started | High
Testing & Quality Assurance | Nina Torres | 2024-06-16 | 2024-07-10 | 35 | QA Lead, Test Automation Engineer | Not Started | High
Training & User Documentation | Ryan Kim | 2024-07-11 | 2024-07-25 | 15 | Training Specialist, Content Writer | Not Started | Medium
Go-Live & Post-Implementation Review | Alex Morgan | 2024-07-26 | 2024-08-05 | 10 | Project Manager, Operations Team | Not Started | High