## Worksheet
Task | Owner | Start Date | End Date | Status | Resources Needed | Priority
Project Initiation | Jane Doe | 2024-03-01 | 2024-03-15 | Completed | Project Manager, Legal Review | High
Resource Assessment | John Smith | 2024-03-16 | 2024-03-31 | In Progress | HR, Finance Team | High
Budget Planning | Lisa Chen | 2024-04-01 | 2024-04-15 | Not Started | Finance, Accounting | Medium
Team Training | Mark Wilson | 2024-04-16 | 2024-05-10 | Not Started | Training Coordinator, IT Support | Medium
Project Launch | Jane Doe | 2024-05-11 | 2024-05-31 | Not Started | All Teams, Marketing | High