## Worksheet
Task | Owner | Start Date | End Date | Status | Resource Allocation | Budget (USD) | Dependencies
Project Initiation | John Doe | 2024-03-01 | 2024-03-15 | In Progress | 1 Full-Time (Project Manager) | $15,000 | Stakeholder Approval
Requirement Gathering | Jane Smith | 2024-03-16 | 2024-04-10 | Planned | 1 Full-Time (Business Analyst) | $18,000 | Project Initiation Complete
Design Phase | Mike Johnson | 2024-04-11 | 2024-05-30 | Pending Approval | 2 Full-Time (UX/UI Team) | $45,000 | Requirement Gathering Complete
Development Phase | Sarah Lee | 2024-06-01 | 2024-08-31 | Not Started | 5 Full-Time (Developers) | $120,000 | Design Phase Complete
Testing & Quality Assurance | David Kim | 2024-09-01 | 2024-10-15 | Planned | 3 Full-Time (QA Team) | $30,000 | Development Phase Complete
Deployment & Go-Live | Lisa Wong | 2024-10-16 | 2024-10-30 | Pending Approval | 1 Full-Time (DevOps) | $15,000 | Testing Phase Complete
Post-Implementation Review | John Doe (Project Manager) | 2024-11-01 | 2024-11-30 | Not Started | Part-Time (Team Lead) | $5,000 | Deployment Complete