## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Resource Required | Priority | Status | Notes
PRJ-001 | Project Initiation Phase | John Doe | 2024-01-01 | 2024-01-15 | 15 | Project Manager, Stakeholder Analyst | High | In Progress | Finalize project charter and scope.
PRJ-002 | Requirements Gathering | Jane Smith | 2024-01-16 | 2024-02-05 | 20 | Business Analyst, UX Designer | High | Planned | Collect and document stakeholder needs.
PRJ-003 | Design Phase | Alex Johnson | 2024-02-06 | 2024-03-15 | 40 | UI/UX Designer, Product Owner | Medium | Not Started | Create wireframes and UI prototypes.
PRJ-004 | Development Phase | Sam Wilson | 2024-03-16 | 2024-05-31 | 85 | Software Developers x4, QA Lead | High | Planned | Implement features according to design.
PRJ-005 | Testing & Quality Assurance | Mia Chen | 2024-06-01 | 2024-06-30 | 30 | QA Team, DevOps Engineer | High | Not Started | Conduct functional and performance testing.