## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Resource Required | Priority | Status | Notes
P-001 | Project Initiation & Scope Definition | John Smith | 2024-03-15 | 2024-03-25 | 11 | Project Manager, Business Analyst | High | On Track | Finalize scope with stakeholders and define deliverables.
P-002 | Stakeholder Requirement Gathering | Sarah Lee | 2024-03-26 | 2024-04-10 | 15 | Business Analyst, UX Designer | High | In Progress | Conduct interviews and workshops with key stakeholders.
P-003 | Feasibility & Risk Assessment | Michael Chen | 2024-04-11 | 2024-04-18 | 8 | Technical Lead, Risk Manager | Medium | Not Started | Assess technical, financial, and operational feasibility.
P-004 | Develop Detailed Project Plan | Emma Wong | 2024-04-19 | 2024-05-05 | 17 | Project Manager, Operations Lead | High | Planned | Include schedule, budget, and resource allocation.
P-005 | Resource Allocation & Team Assignment | David Kim | 2024-05-06 | 2024-05-15 | 10 | HR, Team Leads | Medium | Not Started | Assign team members based on skills and availability.