## Worksheet
Task ID | Task Name | Responsible Person | Start Date | End Date | Duration (Days) | Resource Allocation | Priority Level | Status | Dependencies
PRJ-001 | Project Initiation & Feasibility Study | John Smith | 2024-03-15 | 2024-03-25 | 11 | Project Manager, Business Analysts | High | In Progress
PRJ-002 | Requirements Gathering & Analysis | Emily Chen | 2024-03-26 | 2024-04-15 | 21 | Business Analysts, Stakeholders | High | Not Started | PRJ-001
PRJ-003 | System Design & Architecture Planning | Michael Lee | 2024-04-16 | 2024-05-10 | 25 | Architects, Dev Lead | Medium | Planned | PRJ-002
PRJ-004 | Development Phase - Module 1 | Sarah Kim | 2024-05-11 | 2024-06-15 | 35 | Software Developers, QA Team | High | Not Started | PRJ-003
PRJ-005 | Testing & Quality Assurance | David Brown | 2024-06-16 | 2024-07-10 | 35 | QA Team, Developers | High | Not Started | PRJ-004
PRJ-006 | Deployment & Training Phase | Lisa Wong | 2024-07-11 | 2024-08-15 | 35 | IT Operations, Trainers | Medium | Not Started | PRJ-005
Total Tasks |  |  |  |  | 6 | Report Version: 1.0 ¦ Purpose: Resource Planning ¦ Template Type: Project Plan